Indy Roof Scheduling

Intelligence System

User Manual

Prepared for Indy Roof & Restoration

Version 1.0 — April 2026

CONFIDENTIAL

# Table of Contents

1. Getting Started

2. Initial Setup (Settings)

3. Syncing Jobs from JobNimbus

4. Dashboard Overview

5. Running AI Scoring

6. Map View

7. Weekly Plan (Scheduling)

8. Weather Checks

9. Not Built Workflow

10. Creating & Editing Jobs

11. Troubleshooting

# 1. Getting Started

The Indy Roof Scheduling Intelligence System is a web-based application that helps your scheduling team decide which roofing jobs to build each week. It reads job data from JobNimbus, applies AI-powered scoring and geographic clustering, checks weather conditions, and presents recommended build plans grouped by Project Manager.

Key Principles:

- JobNimbus is always the source of truth — this system never overrides JN data

- Humans make all final scheduling decisions — the AI recommends, you decide

- All decisions are logged with court-admissible notes

- Weather intelligence uses a two-stage system (free API + Clarity Wx/BamWx)

Accessing the Application:

Open your web browser and navigate to the application URL provided by your administrator. The application works on desktop, tablet, and mobile browsers.

# 2. Initial Setup (Settings)

Before using the scheduling system, you need to configure your team and preferences. Click 'Settings' in the left sidebar.

Figure 1: Settings Page — PM Roster Tab

## 2.1 PM Roster

Add your Project Managers who will be assigned to daily build plans.

Step 1: Click the 'PMs' tab in Settings

Step 2: Enter the PM's name, baseline capacity (typical daily jobs), and max capacity (absolute maximum)

Step 3: Click 'Add PM'

| Field | Description |
| --- | --- |
| Name | Project Manager's name (e.g., 'Mike') |
| Baseline | Normal daily job count (e.g., 3). Green zone on capacity bars. |
| Max | Absolute maximum jobs per day (e.g., 5). Red zone if exceeded. |

TIP: Start with your actual PM team. You can adjust baseline/max capacity as you learn the system.

## 2.2 Crew Roster

Add crews with their specialty capabilities. Crews are required for specialty materials like slate, TPO, and wood shake.

## 2.3 Scoring Weights

Configure how much each factor matters when the AI scores and ranks jobs. Use the sliders to adjust weights (0–100).

| Weight | What it Controls |
| --- | --- |
| Days in Queue | Priority for jobs waiting longest (vs. rolling average) |
| Payment Type | Cash jobs score higher than insurance (faster payment) |
| Proximity | Jobs near each other score higher (clustering efficiency) |
| Material-Weather | Jobs with weather-compatible materials score higher |
| Rescheduled | Bump for jobs that were previously not-built |

## 2.4 AI Rules

Write plain-English rules that the AI scoring engine follows. No programming required.

Example: "Prioritize cash payment jobs over insurance. If a job has been in queue more than 60 days, treat it as urgent."

## 2.5 Weather Thresholds

Set temperature, wind, and precipitation limits for each material type.

| Material | Key Thresholds |
| --- | --- |
| Asphalt Shingles | Min 40°F, Max 20mph wind, no rain |
| TPO/EPDM | Min 40°F, Max 15mph wind, 24hr rain window |
| Coatings | Min 50°F, 48hr rain window, max 85% humidity |
| Siding | Max 15mph wind (gust-sensitive) |
| Metal | Min 40°F, Max 15mph wind |

# 3. Syncing Jobs from JobNimbus

The system pulls job data from JobNimbus automatically every 30 minutes. You can also trigger a manual sync.

## 3.1 Manual Sync

Step 1: Go to the Dashboard

Step 2: Click 'Sync JN' in the top-right action bar

Step 3: Wait for the sync to complete (button shows 'Syncing...')

Step 4: A notification appears: 'Synced: X new, Y updated from JN, Z AI-scanned'

What happens during sync:

- New jobs are created with all JN data (customer, address, material, payment, etc.)

- Existing jobs are updated if JN data changed

- New jobs are AI-scanned for duration hints, material type, and permit signals

- Job addresses are geocoded for map plotting

TIP: The AI scan runs only for new jobs to save costs. Already-scanned jobs are never re-scanned.

# 4. Dashboard Overview

The Dashboard is your primary workspace. It shows all jobs organized by status, with tools for scoring, weather checks, and job management.

Figure 2: Dashboard — Job Cards with Bucket Summary

## 4.1 Bucket Summary Cards

Six cards across the top show job counts by status:

| Bucket | Meaning |
| --- | --- |
| To Schedule | Jobs ready to be scheduled (pulled from JN) |
| Scheduled | Jobs assigned to a specific date and PM |
| Primary Complete | Primary trade done, secondary trades may remain |
| Waiting on Trades | Waiting for secondary trades to complete |
| Review | Ready for final review before marking complete |
| Completed | Fully done |

Click any bucket card to filter the job list below.

## 4.2 Job Cards

Each job card displays all scheduling-relevant information:

- Customer name and address

- Material type with duration tier badge (Tier 1/2/3)

- Payment type (green = cash, blue = finance, gray = insurance)

- Days in queue

- Duration (confirmed ✓ or unconfirmed ?)

- AI duration hint (yellow bar if AI detected duration signals)

- JN note preview (job description from JN)

- Weather status badge (Clear / Decision Needed / Do Not Build)

Job Card Actions:

- Click the pencil icon to edit job details

- 'Set Must-Build' — flags a job with a deadline

- 'Confirm Duration' — validates the AI-estimated build duration

- Click the card to expand/collapse full details

## 4.3 Must-Build Jobs

Jobs flagged as Must-Build appear with a red ring and star badge. Must-Build jobs are always scheduled first.

Step 1: Find the job card you need to prioritize

Step 2: Click 'Set Must-Build'

Step 3: Enter a deadline date and reason (e.g., 'Real estate closing April 15')

Step 4: Click 'Flag as Must-Build'

# 5. Running AI Scoring

The scoring engine analyzes all jobs and creates a recommended build plan grouped by Project Manager with geographic clusters.

## 5.1 How to Run Scoring

Step 1: Ensure PMs are configured in Settings (the system will prompt you if not)

Step 2: Click 'Run Scoring' on the Dashboard

Step 3: Wait 15–30 seconds for the AI to analyze all jobs

Step 4: Results appear: AI Explanation, PM Plan Cards, and Job Queue

## 5.2 PM Plan Cards

Each PM gets a card showing their recommended daily load:

- PM name with capacity bar (green = under baseline, yellow = over, red = over max)

- Jobs grouped by cluster with distance info (e.g., 'Cluster 1 — tight • 3 jobs • 1.2mi')

- Standalone jobs listed separately with amber indicator

- Unassigned jobs (overflow beyond PM capacity) shown at bottom

## 5.3 Score Tooltip

Hover over any job's score badge to see the full breakdown: queue time, payment type, proximity, weather compatibility, and other factors.

TIP: After scoring, go to Map View > Build Plan to see the clusters on the map.

# 6. Map View

The Map View shows all jobs plotted on Google Maps with three viewing modes.

Figure 3: Map View — Job Status Mode with Sidebar

## 6.1 Job Status Mode

Default view. Jobs colored by status: Blue = To Schedule, Green = Scheduled, Amber = Standalone, Red = Must-Build.

## 6.2 PM Assignments Mode

After running scoring, colors jobs by assigned PM. Click a PM name in the legend to filter.

## 6.3 Build Plan Mode

The most detailed view. Shows PM > Cluster > Jobs hierarchy in the left panel:

- Click a PM name to zoom to their jobs on the map

- Click a cluster to highlight those specific pins (others fade)

- Each cluster shows tier (tight/close/standard), job count, and max distance

- Click any pin on the map to see full job details

TIP: Build Plan mode auto-activates after scoring. If no scoring has been run, defaults to Job Status.

# 7. Weekly Plan (Scheduling)

The Weekly Plan page is where you build the actual schedule by dragging jobs into days.

## 7.1 Selecting the Week

Step 1: Use the left/right arrows to navigate between weeks

Step 2: The current week shows with date range

## 7.2 Selecting Available PMs

Step 1: Click PM buttons at the top to select who is available this week

Step 2: Selected PMs appear as capacity bars in each day column

Step 3: You must select at least one PM before dragging jobs

## 7.3 Scheduling Jobs

Step 1: Unassigned jobs appear in the left sidebar

Step 2: Drag a job from the sidebar into a day column (Monday–Sunday)

Step 3: The job is assigned to the selected PM and the capacity bar fills

Step 4: A scheduling decision note is automatically generated

Step 5: Drag jobs between days to reschedule

TIP: PM capacity bars turn yellow when over baseline and red when over max capacity.

# 8. Weather Checks

The system uses a two-stage weather architecture to protect scheduled jobs.

## 8.1 Manual Weather Check

Step 1: Click 'Check Weather' on the Dashboard

Step 2: The system checks all scheduled jobs against material thresholds

Step 3: Red banner: Jobs auto-removed due to 'Do Not Build' weather

Step 4: Yellow banner: Jobs needing your decision (marginal conditions)

## 8.2 Scheduler Decision

When weather is marginal, click the yellow 'Decision Needed' badge on the job card:

- 'Include (Override)' — keep the job scheduled despite marginal weather

- 'Exclude (Not Built)' — remove the job and return to queue

## 8.3 Automated Checks

| Check | Time | What It Does |
| --- | --- | --- |
| Morning Check | 6:00 AM | Checks all jobs for today and tomorrow |
| Night-Before | 8:00 PM | Final authority check using Clarity Wx |
| 5am Spot Check | 5:00 AM | Last-minute sanity check on today's builds |

# 9. Not Built Workflow

When a scheduled job cannot be built, mark it as 'Not Built' with a reason.

Figure 4: Not Built Page — Scheduled Jobs with Not Built Actions

## 9.1 Marking a Job as Not Built

Step 1: Go to the 'Not Built' page in the sidebar

Step 2: Find the scheduled job

Step 3: Click 'Not Built' on the job card

Step 4: Select a reason:

| Reason | When to Use |
| --- | --- |
| Weather Pre-Build | Weather turned bad before build day |
| Weather Mid-Build | Weather changed during the build |
| Scope Change | Job scope expanded (needs more days/crew) |
| Crew Unavailable | Assigned crew can't make it |
| Material Issue | Materials not delivered or wrong |
| Customer Related | Customer canceled or rescheduled |
| Other | Any other reason |

The job gets a priority bump (+5 points) and returns to the To Schedule queue.

## 9.2 Standalone Jobs

Jobs located far from all other jobs (>40 miles) are flagged as 'Standalone' with two options:

- Saturday Build — schedule on Saturday when it won't impact weekday clusters

- Sales Rep Managed — hand off to the sales rep to coordinate directly

# 10. Creating & Editing Jobs

## 10.1 Creating a Manual Job

Step 1: Click '+ Create Job' on the Dashboard

Step 2: Fill in: Customer Name, Address, Payment Type, Material Type

Step 3: Optionally add: square footage, sales rep, duration, notes, secondary trades

Step 4: Click 'Create Job'

## 10.2 Editing an Existing Job

Step 1: Find the job card on the Dashboard

Step 2: Click the pencil icon in the top-right corner

Step 3: Edit any field and click 'Save Changes'

TIP: Editing material type or square footage automatically recalculates the duration tier.

# 11. Troubleshooting

| Issue | Solution |
| --- | --- |
| 'No PMs configured' when scoring | Go to Settings > PMs and add at least one PM |
| Jobs not appearing after sync | Wait for sync to complete. Refresh the page. |
| Map not loading | Verify Google Maps API key is set and Maps JavaScript API is enabled in GCP |
| Weather shows 'No data' | Jobs need lat/lng coordinates. Re-sync or edit the address. |
| Scoring takes too long | Normal: 15-30 seconds. Check Anthropic API key if it fails. |
| Drag-drop not working | Select at least one PM from the buttons at the top. |
| Need a fresh start | Settings > System > 'Reset Database' |

Support:

For technical issues, contact your system administrator.